## DELIVER
PROJECT: | CONCERTO
DATE: | 2024-07-31
MONTH: | JULY
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
BST_SPRINT_34 | 16 | 54 | ENDED
BST_SPRINT_35 | 13 | 52 | STARTED
NOTES
During the month of July, BST team had the chance to deliver the scope of Sprint 34 in Production
Also, started the development of Sprint 35 in Dev Environment
DELIVERIES
IMAGE | IMAGE | IMAGE
NOTES
TEXTO PARA IMAGENS
TEXTO PARA IMAGENS
BACKLOG
TICKETS | ESTIMATED | NOT ESTIMATED | % ESTIMATED | % NOT ESTIMATED | STORYPOINTS | SPRINT STORYPOINTS | BACKLOG SPRINTS
81 | 62 | 19 | 76.54% | 23.46% | 292 | 60 | 4.8667
NOTES
Based on the current numbers of presented above, BST team has 5 sprint in backlog.
Its important to highlight that still 23% of the listed tickets are not estimated, so the workload is higher then this
I would like to thanks to everyone involved on the project, withouth you the above could not be possible.

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
ENDED
ACHIEVED
NOT ACHIEVED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER