## DELIVER
PROJECT: | CONCERTO
DATE: | 2024-08-01
MONTH: | AUGUST
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
BST_SPRINT_34 | 16 | 54 | ENDED
BST_SPRINT_35 | 13 | 52 | STARTED
NOTES
During the month of July, BST team had the chance to work the scope of Sprint 34 in Production and start the development of Sprint 35.
Regarding the release of this two sprints, will be ok the week of 19th of August, waiting for the final date to open the RTC change request.
DEPLOYMENTS
ENVIRONMENT | EXPECTED DATE
PROD | Week of 19th August
WAITING FOR DEPLOYMENT
JIRA | DESCRIPTION | PRIORITY
BST-1715 | Modify the JOB Refresh_inst_for_Fund_Subfund_Share_input | CRITICAL
BST-1710 | [Mapping PTFINventory] - Ratings REGRESSION | CRITICAL
BST-1711 | Performance > PTF message mapping duration analyse and potential improvments | BLOCKER
BST-1712 | Performance >> GetRefInstmds Call review > Frequency | BLOCKER
BST-1713 | [Mapping PtfInventory] - Cash_Category_1 et Cash_Categorie_2 - CTO-1962 | CRITICAL
BST-1714 | Rename the JOB testTopAlto to PTFINV_mapping_from_INST_receiving | MAJOR
BST-1694 | [Mapping PtfInventory] - Cash_Category_1 et Cash_Categorie_2 - CTO-2055 | BLOCKER
BST-1700 | [Mapping CFI_CODE] - Kondor IRS - CTO-2069 | MAJOR
BST-1704 | [Mapping Asset] - Quote => InstrumentNetPrice Mapping modified for priority 3 | MAJOR
BST-1611 | JOB getRefInstMDS running to error due to time | MAJOR
BST-1666 | [ASSET] attribute.Flag_AutoCall for CFICODE_ like 'D%' Linked with CTO-1993 | CRITICAL
BST-1671 | bst_workflowmonitoring additional input devices to log | CRITICAL
BST-1718 | [Mapping Portfolio] - UMBRELLA_NAME KO | BLOCKER
BST-1721 | [BST PROD]: Instrument Contract SWAP not mapped | BLOCKER
BST-1722 | [COLLAT] - Mapping UnderlyingQty Asset | BLOCKER
BST-1723 | [COLLAT- Cash ou Securities] problem on the mapping of bst_inventory | MAJOR
BST-1725 | [Mapping Portfolio] Problem in PROD Mapping bst_portfoliotoalto_valuation and bst_portfoliotoalto_quotation | BLOCKER
BST-1716 | TOP UMBRELLA Issue | BLOCKER
BST-1736 | [API ASSET] - Quotation.netPrice - InstrumentNetPrice | BLOCKER
NOTES
List of tickets from Sprint 34 already on PREPROD environment, waiting for the next Production Release.
IMAGE0
In this picture above we can see the the amont of tickets delivered on the last sprints.
DELIVERIES
IMAGE1
IMAGE2
NOTES
Regarding Sprint 34, even thought BST team has over passed the goal of 56 Storypoints planned for the sprint, reaching 60 Storypoints , its important to highlight that some of the planned tickets were not completely finished on the sprint window but achieved in the meantime.
In the meantime, while debuging and better analysis, BST team had the chance to work in some other smaller tickets that made possible the deliver of 119%.
BACKLOG
TICKETS | ESTIMATED | WAITING | NOT ESTIMATED | STORYPOINTS | BACKLOG SPRINTS
91 | 72 | 10 | 19 | 349 | 6
CHART
IMAGE3
IMAGE4
In terms of backlog, highlight for the 68% of topics in Production and the 18% of listed tickets for Performance Scope.
We can also check the current difference between ACR and Defects, where 13 were created in the last couple of days. For the future, we will share as well how many we create per month.
ANUAL CHART
IMAGE5
Based on the chart, we can see that since Sprint 22, BST team have reached a higher maturity, ensuring the delivery of the planned scope.
GREETINGS
I would like to thanks to everyone involved on the project, withouth you the above could not be possible.

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
ENDED
ACHIEVED
NOT ACHIEVED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER