## DELIVER
PROJECT: | COMPASS
DURATION: | 2024-12-02 | TO | 2024-12-13
MONTH: | DECEMBER
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
CMP_SPRINT_35 | 12 | 13.5 | STARTED
NOTES
During the resolution of Sprint 35, Compass Core team will work on some mandatory tickets in order to solve the Revenue Business Line Step 2, corrections on the metadatas regarding BCT, MERCURY and MNI, correction of some frontend bugs and finally the historisation.
EXPECTED DATES OF DEPLOYMENT
QUAL | PREPROD | PROD
Constant Iteractions | Constant Iteractions | December 21st
NOTES
Deployments will be delivered as soon as code is available.
DEVELOPMENT AND SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS | STORY POINTS | COMMENTS | CRITICITY
DEFECT | CMP-418 | Historisation - 4th and above New version creation should not be possible |  |  |  | MAJOR
STORY | CMP-282 | Test Automation - 1º Test Case |  |  |  | MAJOR
DEFECT | CMP-450 | Periods end in 202412 |  |  |  | TRIVIAL
DEFECT | CMP-389 | GUI - Key Active Flag |  |  |  | MAJOR
DEFECT | CMP-402 | KValue Integration and Data Acquisition Status details |  |  |  | MINOR
STORY | CMP-454 | RevBL step 2 - exclude certain PNL ITEM from step 2 allocation |  |  |  | MAJOR
DEFECT | CMP-456 | Historisation of month modifies also historical data on previous months |  |  |  | MAJOR
DEFECT | CMP-308 | MNI_MNI : Incorrect Table Metadata |  |  |  | CRITICAL
DEFECT | CMP-309 | MERCURY_MERCURY : Incorrect Table Metadata |  |  |  | MINOR
DEFECT | CMP-310 | CALCULATION_REVCLISTEP3 : Incorrect Table Metadata |  |  |  | MINOR
DEFECT | CMP-311 | CALCULATION_KVALUE : Incorrect Table Metadata |  |  |  | MINOR
DEFECT | CMP-312 | BCT_BCT : Incorrect Table Metadata |  |  |  | MINOR
MINOR
NOTES
Metadata fix regarding the BCT, MERCURY and MNI sources will be handled by Jean Verducci
Creation of documentation based on the current scope, to be delivered until the last day of sprint.
ANALYSE AND TESTING
PRIORITY | JIRA | DESCRIPTION | STATUS | ACTION | COMMENTS
NOTES
METRICS
IMAGE1
IMAGE2
NOTES
DEFINITION OF GOALS
Development and testing of the scope until last day of Sprint in order to have the necessary approvals for the release of December 21st 2024.
GREETINGS
I would like to thanks to everyone involved on the project, withouth you the above could not be possible.

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBER