## DELIVER
PROJECT: | COMPASS
DURATION: | 2024-07-15 | TO | 2024-08-02
MONTH: | JULY
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
CMP_SPRINT_30 | 4 | 48 | STARTED
NOTES
Development of 3 tickets from Sprint 29 [ CMP-413. CMP-390 and CMP-424 ]
Focus on documentation [CMP-424] and training to be acquired on the frontend side.
EXPECTED DATES OF DEPLOYMENT
QUAL | PREPROD | PROD
2024-08-05 | 2024-08-08 | 2024-08-24
NOTES
Deployments will be delivered as soon as code is available. The current date of 5th of August is the deadline date for the full scope to be delivered on QUAL.
Package to be frozen for the next release on Production.
DEVELOPMENT AND SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS | STORY POINTS | COMMENTS | ORDER
STORY | CMP-424 | Compass - Creation of Documentation | DEVELOPMENT | 5 | Ticket from SP29 - To be delivered first week of the sprint | 1
STORY | CMP-413 | Enhancement - specific steps to map old cost centers to new business unit hierarchy | DEVELOPMENT | 20 |  | 2
STORY | CMP-423 | Enhancement - specific steps to map old cost centers to new business unit hierarchy - Costs | WAITING | 20 |  | 2
DEFECT | CMP-390 | GUI - CmPCCOPE Active Flag and Table | WAITING | 3 |  | 3
NOTES
For this sprint scope, one good milestone we propose to achieve is the delivery of the documentation.
In terms of enhancements, [CMP-413 and CMP-423] will provide better results and quality to the application.
ANALYSE AND TESTING
PRIORITY | JIRA | DESCRIPTION | STATUS | ACTION | COMMENTS
DEFECT | CMP-406 | duplicates in 'RefPnlItem' | UAT | TEST | Test will be performed on PREPROD
DEFECT | CMP-393 | GUI -Rules CmpCC Level missing | UAT | TEST | Test will be performed on PREPROD
DEFECT | CMP-412 | Calculation GUI : differentiate button rev by client from calculate all / revenue by BL only start rev by BL | UAT | TEST | Test will be performed on PREPROD
DEFECT | CMP-377 | 404 Error into RefThirdParty | UAT | TEST | Test will be performed on PREPROD
DEFECT | CMP-431 | KEYS -Newly created keys shall be defaulted to KEYACTVFLG_ = 1 | UAT | TEST | Test will be performed on PREPROD
NOTES
In order to have na efficient sprint, we will test the above tickets. This will provide us a more accurate view on the current backlog and next topics to handle.
DEFINITION OF GOALS
Preparation of release on 24th August. Work on scope to be delivered.
Delivery of documentation. (CMP-424)
Creation of US for Uplouad of Rules and Dashboard Behaviour
Write the new US related to Top Transaction Banking ¦ Select PNL Item to aplly for step 2 VER BY BL ¦
Learning curve on Frontend side

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER