## DELIVER
PROJECT: | CONCERTO
DURATION: | 2024-07-15 | TO | 2024-08-02
MONTH: | JULY
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
CMP_SPRINT_30 | 5 | 54 | STARTED
NOTES
Development of 2 tickets (mention ticket IDs if possible)
Knowledge transfer and documentation updates
EXPECTED DATES OF DEPLOYMENT
QUAL | PREPROD | PROD
TO BE CONFIRMED | TO BE CONFIRMED | TO BE CONFIRMED
NOTES
For the scope of Sprint 29 we've raised the following priorities:
DEVELOPMENT AND SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS | STORY POINTS | COMMENTS | ORDER
STORY | BST-1715 | Modify the JOB Refresh_inst_for_Fund_Subfund_Share_input | TO START DEVELOPMENT |  |  | DOCUMENTATION
CHANGE REQUEST | BST-1710 | [Mapping PTFINventory] - Ratings REGRESSION | TO START DEVELOPMENT |  |  | TRAINING
DEFECT | BST-1711 | Performance > PTF message mapping duration analyse and potential improvments | TO START DEVELOPMENT |  |  | 1
DEFECT | BST-1712 | Performance >> GetRefInstmds Call review > Frequency | DEVELOPMENT |  |  | 2
DEFECT | BST-1713 | [Mapping PtfInventory] - Cash_Category_1 et Cash_Categorie_2 - CTO-1962 | UAT |  |  | 3
DEFECT | BST-1714 | Rename the JOB testTopAlto to PTFINV_mapping_from_INST_receiving | IT ADM TEST |  |  | 4
NOTES
For the scope of Sprint 29 we've raised the following priorities:
ANALYSE AND TESTING
PRIORITY | JIRA | DESCRIPTION | STATUS | ACTION | COMMENTS
DEFECT | CMP-100 | BCT SCOPE | WAITING | TEST | Test on different environments
STORY | CMP-100 | BS | IT ADM | GROOMING | TESTE
NOTES
Development of 2 tickets (mention ticket IDs if possible)
Knowledge transfer and documentation updates
DEFINITION OF GOALS
RELEASE ON PRODUCTION ENVIRONMENT
RELEASE ON PRODUCTION ENVIRONMENT
RELEASE ON PRODUCTION ENVIRONMENT
RELEASE ON PRODUCTION ENVIRONMENT
RELEASE ON PRODUCTION ENVIRONMENT
RELEASE ON PRODUCTION ENVIRONMENT

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER