## DELIVER
PROJECT: | COMPASS
DATE: | 2024-11-08
MONTH: | NOVEMBER
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
CMP_SPRINT_33 | 8 | 20 | ENDED
NOTES
For SPRINT 33 we've planned 8 tickets that solves some automation tests and some functional view for the end users.
DEFINITION OF GOALS
GOALS | EXPECTED | STATUS
Grooming on CMP-417 | 2024-11-08 | ACHIEVED
Reach last day of sprint with everything tested on all Non-Prod Environments | 2024-11-08 | CLOSED
NOTES
Grooming on CMP-417 achieved with estimation raised and planned the first part for the Sprint 34
METRICS
IMAGE1
IMAGE2
NOTES
Deployment in PROD environment planned to November 23th
Package closed on PREPROD environment, waiting for the release on PROD.
PLANNED SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS
STORY | CMP-438 | Upload of rules as batch process | GO FOR PRODUCTION
DEFECT | CMP-439 | Map old cost centers to new business unit hierarchy - Costs and Revenues should use same rules | GO FOR PRODUCTION
DEFECT | CMP-326 | One rule can use only one key | GO FOR PRODUCTION
DEFECT | CMP-448 | Impossible to save new operational CC parameterization in GUI | GO FOR PRODUCTION
DEFECT | CMP-429 | CmpCCOPE Perimeter - Add an OPE Business Line no longer possible | GO FOR PRODUCTION
DEFECT | CMP-440 | CLONE - RefKeyTyp and RefCalcProc tables -Edit or Delete actions shall not be available (GUI) | GO FOR PRODUCTION
STORY | CMP-446 | Calculation automatic FTE KEY - add CC exclusions | GO FOR PRODUCTION
DEFECT | CMP-451 | key values creation screen | GO FOR PRODUCTION
NOTES
ADDED SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS
NOTES
ANALYSE AND TESTING
PRIORITY | JIRA | DESCRIPTION | STATUS
NOTES
GREETINGS
I would like to thanks to everyone involved on the project, withouth you the above could not be possible.

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
ENDED
ACHIEVED
NOT ACHIEVED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER