## DELIVER
PROJECT: | COMPASS
DURATION: | 2024-08-12 | TO | 2024-08-30
MONTH: | AUGUST
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
CMP_SPRINT_31 | 19 | 50 | STARTED
NOTES
Release on Production on 26th July.
Intermediary releases during the sprint, in order to achieve a smooth transition and tests between environments.
EXPECTED DATES OF DEPLOYMENT
QUAL | PREPROD | PROD
Not expected | Not expected | To be discussed
NOTES
Deployments will be delivered as soon as code is available.
DEVELOPMENT AND SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS | STORY POINTS | COMMENTS | CRITICITY
NOTES
Based on August holidays, for Sprint 31 we will not deliver any new development or bug fixing.
On the other hand, Compass Core Team will fully test the below tickets in order to be included on the next release in PROD.
ANALYSE AND TESTING
PRIORITY | JIRA | DESCRIPTION | STATUS | ACTION | COMMENTS
STORY | CMP-437 | Analyse and Tests for Sprint 31 | WAITING | TEST
STORY | CMP-119 | Calculations : BL Revenue Step 2 | UAT | TEST
STORY | CMP-242 | RevBL - GUI modification to allow RevBL launch and visualisation | UAT | TEST
STORY | CMP-120 | Calculations : BL Revenue Step 3 | UAT | TEST
DEFECT | CMP-361 | FTE Keys missing from CALCULATION_KVALUE table | UAT | TEST
DEFECT | CMP-367 | Rev BL Step 3 - The system shall apply only key values, which are applicable on the calculated period | UAT | TEST
STORY | CMP-384 | Define model for storing monthly results (historisation) - GOI by BusLine | IT ADM TEST | TEST
STORY | CMP-413 | Enhancement - specific steps to map old cost centers to new business unit hierarchy | UAT | TEST
STORY | CMP-423 | Enhancement - specific steps to map old cost centers to new business unit hierarchy - Costs | WAITING | TEST
STORY | CMP-416 | Enhancement - add Step 3 to Cost by BL | UAT | TEST
STORY | CMP-16 | GUI: Screen Overview | UAT | TEST
DEFECT | CMP-412 | Calculation GUI : differentiate button rev by client from calculate all / revenue by BL only start rev by BL | UAT | TEST
DEFECT | CMP-408 | Delete of a historized version should provoke a physical delete of data | UAT | TEST
DEFECT | CMP-407 | Problem uploading multiple keys in KValue integration | UAT | TEST
DEFECT | CMP-399 | GUI -KValue Integration File name missing | UAT | TEST
STORY | CMP-386 | Show warning message to the user launching an export > 1000 kvalues | UAT | TEST
STORY | CMP-109 | Data Load : Compass Cost Centers Computation | UAT | TEST
STORY | CMP-68 | Data Load: AUA Input | UAT | TEST
DEFECT | CMP-405 | Negative key values impossible in the GUI | UAT | TEST
NOTES
METRICS
NOTES
In order to have na efficient sprint, we will test the above tickets. This will provide us a more accurate view on the current backlog and next topics to handle.
DEFINITION OF GOALS
Plan the release of 24th of August 2024
Documentation and Grooming Sessions on CMP-436
GREETINGS
I would like to thanks to everyone involved on the project, withouth you the above could not be possible.

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER