## DELIVER
PROJECT: | CONCERTO
DATE: | 2024-07-31
MONTH: | JULY
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
BST_SPRINT_34 | 16 | 54 | ENDED
BST_SPRINT_35 | 13 | 52 | STARTED
NOTES
During the month of July, BST team had the chance to deliver the scope of Sprint 34 in Production
Also, started the development of Sprint 35 in Dev Environment
DEPLOYMENTS
ENVIRONMENT | EXPECTED DATE
PROD | 2024-08-24
WAITING FOR DEPLOYMENT
PRIORITY | JIRA | DESCRIPTION
DEFECT | BST-1715 | Modify the JOB Refresh_inst_for_Fund_Subfund_Share_input
DEFECT | BST-1710 | [Mapping PTFINventory] - Ratings REGRESSION
DEFECT | BST-1711 | Performance > PTF message mapping duration analyse and potential improvments
DEFECT | BST-1712 | Performance >> GetRefInstmds Call review > Frequency
DEFECT | BST-1713 | [Mapping PtfInventory] - Cash_Category_1 et Cash_Categorie_2 - CTO-1962
DEFECT | BST-1714 | Rename the JOB testTopAlto to PTFINV_mapping_from_INST_receiving
ACR | BST-1694 | [Mapping PtfInventory] - Cash_Category_1 et Cash_Categorie_2 - CTO-2055
ACR | BST-1700 | [Mapping CFI_CODE] - Kondor IRS - CTO-2069
ACR | BST-1704 | [Mapping Asset] - Quote => InstrumentNetPrice Mapping modified for priority 3
DEFECT | BST-1611 | JOB getRefInstMDS running to error due to time
ACR | BST-1666 | [ASSET] attribute.Flag_AutoCall for CFICODE_ like 'D%' Linked with CTO-1993
ACR | BST-1671 | bst_workflowmonitoring additional input devices to log
DEFECT | BST-1718 | [Mapping Portfolio] - UMBRELLA_NAME KO
DEFECT | BST-1721 | [BST PROD]: Instrument Contract SWAP not mapped
ACR | BST-1722 | [COLLAT] - Mapping UnderlyingQty Asset
DEFECT | BST-1723 | [COLLAT- Cash ou Securities] problem on the mapping of bst_inventory
DEFECT | BST-1725 | [Mapping Portfolio] Problem in PROD Mapping bst_portfoliotoalto_valuation and bst_portfoliotoalto_quotation
DEFECT | BST-1716 | TOP UMBRELLA Issue
DEFECT | BST-1736 | [API ASSET] - Quotation.netPrice - InstrumentNetPrice
DELIVERIES
IMAGE1
IMAGE2
NOTES
Regarding Sprint 34, even thought BST team has reached the goal of 56 Storypoints planned for the sprint, its important to highlight that some of the planned tickets were not completely finished.
In the meantime, while debuging and better analysis, BST team had the chance to work in some other smaller tickets that made possible the deliver of 106%.
BACKLOG
TICKETS | ESTIMATED | WAITING | NOT ESTIMATED | STORYPOINTS | BACKLOG SPRINTS
81 | 62 | 10 | 19 | 292 | 5
CHART
IMAGE3
IMAGE4
In terms of backlog, highlight for the 7% of topics in Production and the 70% of listed tickets for French Scope.
ANUAL CHART
IMAGE5
Based on the chart, we can see that since Sprint 22, BST team have reached a higher maturity, ensuring the delivery of the planned scope.
GREETINGS
I would like to thanks to everyone involved on the project, withouth you the above could not be possible.

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
ENDED
ACHIEVED
NOT ACHIEVED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER