## DELIVER
PROJECT: | CONCERTO
DURATION: | 2024-07-22 | TO | 2024-08-09
MONTH: | JULY
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
BST_SPRINT_35 | 13 | 50 | STARTED
NOTES
Release on Production on 26th July.
Intermediary releases during the sprint, in order to achieve a smooth transition and tests between environments.
EXPECTED DATES OF DEPLOYMENT
QUAL | PREPROD | PROD
2024-08-09 | 2024-08-12 | 2024-08-16
NOTES
Deployments will be delivered as soon as code is available.
The current date of 5th of August is the deadline date for the full scope to be delivered on QUAL.
DEVELOPMENT AND SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS | STORY POINTS | COMMENTS | CRITICITY
DEFECT | BST-1729 | [COLLAT] - Mapping CPTCDTMP KO | DEVELOPMENT | 5 |  | BLOCKER
ACR | BST-1730 | [Mapping Portfolio] - LevelPrestation - Update BST_PORTFOLIO_ISLIQUIDATED V8 | TO START DEVELOPMENT | 3 |  | CRITICAL
DEFECT | BST-1727 | [BST] Mapping status monitoring | TO START DEVELOPMENT | 5 |  | CRITICAL
DEFECT | BST-1728 | Node crashing in the morning + logs error while restarting | TO START DEVELOPMENT | 5 | Assigned to Zied. Waiting for feedback from BST-1711 (SP34). Will be deployment on PROD on 26.07 | BLOCKER
ACR | BST-1719 | Adding new data in BST_REF_VAL from XML message id_bb_company linked with CTO-1934 | TO START DEVELOPMENT | 3 |  | CRITICAL
ACR | BST-1720 | [Mapping] Fx rate null for a currency not to mapped in ssettoalto_currency_quotations linked with CTO-2060 | TO START DEVELOPMENT | 3 |  | MAJOR
ACR | BST-1717 | [Mapping Asset] - CFI_CODE - CTO-2110 | TO START DEVELOPMENT | 3 |  | MAJOR
ACR | BST-1732 | [API ISSUER] - asAtDate to removed | TO START DEVELOPMENT | 1 |  | MAJOR
ACR | BST-1733 | Overriding values: message error | TO START DEVELOPMENT | 5 |  | MAJOR
DEFECT | BST-1734 | Overriding values: Third party name | TO START DEVELOPMENT | 5 |  | MAJOR
ACR | BST-1687 | Overriding values: import NEW VALUE format ERROR | TO START DEVELOPMENT | 5 |  | CRITICAL
DEFECT | BST-1664 | [COLLAT] - INTEGRATION FILE - PROD | TO START DEVELOPMENT | 5 |  | CRITICAL
DEFECT | BST-892 | [API Codification-Groups] - Update Palmyra | IT ADM TEST | 2 |  | MAJOR
NOTES
For this sprint scope, one good milestone we propose to achieve is the delivery of the documentation.
In terms of enhancements, [CMP-413 and CMP-423] will provide better results and quality to the application.
ANALYSE AND TESTING
PRIORITY | JIRA | DESCRIPTION | STATUS | ACTION | COMMENTS
DEFECT | BST-1352 | [API Diffusion-lists] - KO PROD/PREPROD | DEVELOPMENT | TEST | Test needs to be performed, in order to see if the problem still persists
NOTES
In order to have na efficient sprint, we will test the above tickets. This will provide us a more accurate view on the current backlog and next topics to handle.
METRICS
IMAGE1
IMAGE2
NOTES
In order to have na efficient sprint, we will test the above tickets. This will provide us a more accurate view on the current backlog and next topics to handle.
DEFINITION OF GOALS
SP34 full tested and released on PROD on 26th of July.
Backlog refinement with BA team. Currently 26% of tickets not estimated or missing informations.
GREETINGS
I would like to thanks to everyone involved on the project, withouth you the above could not be possible.

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER