## DELIVER
PROJECT: | CONCERTO
DURATION: | 2024-06-27 | TO | 2024-07-12
MONTH: | JULY
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
CMP_SPRINT_29 | 20 | 30 | STARTED
NOTES
Development of 2 tickets (mention ticket IDs if possible)
Knowledge transfer and documentation updates
EXPECTED DATES OF DEPLOYMENT
QUAL | PREPROD | PROD
TO BE CONFIRMED | TO BE CONFIRMED | TO BE CONFIRMED
NOTES
For the scope of Sprint 29 we've raised the following priorities:
DEVELOPMENT AND SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS | STORY POINTS | COMMENTS | ORDER
STORY | BST-1715 | Modify the JOB Refresh_inst_for_Fund_Subfund_Share_input | TO START DEVELOPMENT | 10 | Creation of documentation for features to be worked on this sprint | DOCUMENTATION
CHANGE REQUEST | BST-1710 | [Mapping PTFINventory] - Ratings REGRESSION | TO START DEVELOPMENT | 5 | Knowledge transfer - UI Fron-End | TRAINING
DEFECT | BST-1711 | Performance > PTF message mapping duration analyse and potential improvments | TO START DEVELOPMENT | 10 |  | 1
DEFECT | BST-1712 | Performance >> GetRefInstmds Call review > Frequency | DEVELOPMENT | 8 |  | 2
DEFECT | BST-1713 | [Mapping PtfInventory] - Cash_Category_1 et Cash_Categorie_2 - CTO-1962 | UAT | 5 |  | 3
DEFECT | BST-1714 | Rename the JOB testTopAlto to PTFINV_mapping_from_INST_receiving | IT ADM TEST | 10 |  | 4
NOTES
For the scope of Sprint 29 we've raised the following priorities:
ANALYSE AND TESTING
PRIORITY | JIRA | DESCRIPTION | STATUS | ACTION | COMMENTS
DEFECT | CMP-100 | BCT SCOPE | WAITING | TEST | Test on different environments
STORY | CMP-100 | BS | IT ADM | GROOMING | TESTE
NOTES
Development of 2 tickets (mention ticket IDs if possible)
Knowledge transfer and documentation updates
DEFINITION OF GOALS
RELEASE ON PRODUCTION ENVIRONMENT
Start to prepare release on PROD environment - August 2024
CREATION AND ANALYSE OF US
Write the new US related to Top Transaction Banking ¦ Select PNL Item to aplly for step 2 VER BY BL
Creation of US for Uplouad of Rules
BRAINSTORM
Brainstorm on Monitoring and Performance topics

## AUTOMATION
PROJECT NAME |  |  | DATES
| SIGLA | PROJECT | MONTH
| CMP | COMPASS | JANUARY
| BST | CONCERTO | FEBRUARY
MARCH
APRIL
MAY
JUNE
JULY
AUGUST
SEPTEMBER
OCTOBER
NOVEMBER
DECEMBBER