## DELIVER
PROJECT: | COMPASS
DURATION: | 2024-11-11 | TO | 2024-12-02
MONTH: | DECEMBBER
RESUME
SPRINT | EXPECTED TICKETS | STORY POINTS | STATUS OF SPRINT
CMP_SPRINT_34 | 24 | 41 | STARTED
NOTES
During the resolution of Sprint 34, Compass Core team will work on some mandatory tickets in order to solve the Automation Tests Flow, corrections on the metadatas regarding SIRIUS, correction of some frontend bugs and finally the first part of the new US CMP-417
EXPECTED DATES OF DEPLOYMENT
QUAL | PREPROD | PROD
Constant Iteractions | Constant Iteractions | To be discussed
NOTES
Deployments will be delivered as soon as code is available.
DEVELOPMENT AND SCOPE
PRIORITY | JIRA | DESCRIPTION | STATUS | STORY POINTS | COMMENTS | CRITICITY
DEFECT | CMP-421 | CLONE - Calculation -Period input in the Period search box not possible | DEVELOPMENT | 3 |  | MAJOR
DEFECT | CMP-432 | Calculation launch process timing in GUI screen is 2H before | TO START DEVELOPMENT | 2 |  | MAJOR
DEFECT | CMP-160 | Bug GUI ACQ : question mark description | UAT | 1 |  | TRIVIAL
CHANGE REQUEST | CMP-441 | GUI -Historisation: Failed or In Progress shall be notified to the user | TO START DEVELOPMENT | 5 |  | MAJOR
DEFECT | CMP-452 | Erroneous label for Cost Centre Code in CCPerimeter | UAT | 1 |  | MINOR
STORY | CMP-422 | Training on GUI framework and deplyoment | DEVELOPMENT | 0 |  | MAJOR
STORY | CMP-417 | Enhancement - GUI of LDD / BCT / branch links to allow AUC allocation in step 4 | TO START DEVELOPMENT | 8 |  | MAJOR
DEFECT | CMP-443 | Mercury table allows duplicate active 'comercialcustomercode_' on loading | TO START DEVELOPMENT | 5 |  | CRITICAL
DEFECT | CMP-292 | SIRIUS_REFSERVCNTR : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-293 | SIRIUS_REFMETRIC : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-294 | SIRIUS_REFPNLITEM : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-295 | SIRIUS_REFFACT : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-296 | SIRIUS_REFENTITY : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-297 | SIRIUS_REFBLPNLTYPE : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-298 | SIRIUS_REFBLL2 : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-299 | SIRIUS_REFBLL1 : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-300 | SIRIUS_PNLTYPE : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-301 | SIRIUS_PNLITEMD : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-302 | SIRIUS_PNLITEMC : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-303 | SIRIUS_PNLITEMB : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-304 | SIRIUS_PNLITEMA : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-305 | SIRIUS_PNL : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-306 | SIRIUS_FTEAVG : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
DEFECT | CMP-307 | SIRIUS_FTE : Incorrect Table Metadata | TO START DEVELOPMENT | 0.5 |  | MINOR
NOTES
Metadata fix regarding the SIRIUS source will be handled by Jean Verducci
Creation of documentation based on the current scope, to be delivered until the last day of sprint.
ANALYSE AND TESTING
PRIORITY | JIRA | DESCRIPTION | STATUS | ACTION | COMMENTS
STORY | CMP-428 | Indicator and alert when other computation processes are running | TO START DEVELOPMENT | GROOMING
CHANGE REQUEST | CMP-441 | GUI -Historisation: Failed or In Progress shall be notified to the user | TO START DEVELOPMENT | GROOMING
NOTES
Regarding the two listed tickets, the first one (CMP-428) will be groomed, in order to clarify some points for development phase.
The second ticket (CMP-441) necessary some clarifications between Pedro Almeida and Jean Verducci in order to achieve the goal of the Change Request.
METRICS
IMAGE1
IMAGE2
NOTES
DEFINITION OF GOALS
UMS Request for Nominal Accounts creation
Creation of ticket for "Exclude Net Interest Margins In Step 2"
Nominal Accounts for different environments (DEV, QUAL, PREPROD)
GREETINGS
I would like to thanks to everyone involved on the project, withouth you the above could not be possible.

## AUTOMATION
PROJECT NAME |  |  | STATUS OF THE SPRINT
Insert new fields as needed. Remember that needs to be included and updated on the "DELIVER" sheet.
SIGLA | PROJECT |  | PLANNING_START_END
CMP | COMPASS |  | NOT STARTED
BST | CONCERTO |  | STARTED
CLOSED
TYPE OF PRIORITY |  | DATES | STATUS OF THE TICKETS
TYPE |  | MONTH | STATUS
STORY |  | JANUARY | TO START DEVELOPMENT
ACR |  | FEBRUARY | WAITING
CHANGE REQUEST |  | MARCH | DEVELOPMENT
DEFECT |  | APRIL | IT ADM
TASK |  | MAY | UAT
|  | JUNE | GO FOR PRODUCTION
|  | JULY | RELEASED IN PRODUCTION
|  | AUGUST | CANCELLED
|  | SEPTEMBER | CLOSED
OCTOBER
NOVEMBER
DECEMBBER